## Advocacy 1
AAUW Whatcom Branch
SMART Goal - Advocacy #1
In order to further develop citizenship and achieve pay equity in the community, we will promote and facilitate opportunities for young women to attend either SmartStart or WorkSmart.
By the end of FY 20-21, we will have held at least one SmartStart or WorkSmart event in the community, either on our own or in partnership with another organization/college/university.
This event could be either an in-person session or a group online event. We will measure the impact by surveying attendees within one year of event attendance.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
|  | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
Advocacy | Hold one Smart Start or Work Smart no later than by June 2021 | Train one instructor - complete | Talk to Whatcom and BTC about holding event | Choose potential partner | Choose venue | Advertise event | Hold first event | Survey participants | Follow up survey of participants
|  | Brainstorm possible hosts/venues | Put funding in budget | Determine logistics requrirements | Choose date |  | Obtain permission for survey contact
Research license/other costs

## Philanthropy 1
AAUW Whatcom Branch
SMART Goal - Philanthropy 1
In order to raise additional funds needed to support our educational, advocacy and philanthropic priorities, we will create a signature fundraiser by the end of FY21, to be held no later than
the end of CY 2022. The event will be one that can be accomplished with our membership resources, possibly in collaboration with another local women’s organization.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Create a signature fundraiser by end of CY 2020 to be held not later than end of CY 2022 | Begin brainstorming ideas and create a list | Begin looking for committee members | Assign committee chair | Narrow down ideas |  | Present options to board by June 2021 |  | Hold event
|  |  |  | Begin looking at ideas | Contact potential sponsors for feasibility assessment |  | Obtain agreement to participate pending board approval from other collaborating organization(s)
|  | end of March | end of April | end of May | end of August |  |  |  | end of Feb 22
[5 empty] | Contact other organizations to collaborate with |  | Board selects fundraiser
Begin planning
beginning of FY 21-22

## Philanthropy 2
AAUW Whatcom Branch
SMART Goal - Philanthropy 2
In order to facilitate fundraising to support our educational, advocacy, and philanthropic priorities, by the end of FY 20-21, we will expand our branch’s 501c3 status to include more programs than Tech Trek.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Expand branch 501C3 status | Decide with board what level of 501C3 we should pursue (branch, foundation, etc.) | Meet with Stanwood Camano | Complete initial draft of forms required | Submit forms to IRS | Once approved develop language to go in our fundraising materials
|  | Contact Stanwood Camano to set up meeting | Assign form completion responsibility
|  | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
Obtain copy of forms and instructions

## Membership 1
AAUW Whatcom Branch
Smart Goal - Membership 1
In order to ensure a vital membership, we will maintain our membership numbers throughout FY 20-21 and FY 20-22, with the stretch goal of increasing our membership from 70 to 80.
A vital membership will allow us to have the headcount needed to achieve our educational, philanthropic and advocacy missions. We will achieve this by holding new membership events,
a yearly October luncheon, and assigning buddies to new members. Look for ways to enhance memership experience for those who aren't active in meetings and interest groups
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Maintain membership numbers throughout FY 20-21 and 21-22 with stretch goal of increasing to 80 | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
|  | Develop "buddy" roles | Solicit buddies |  | Plan October luncheon | hold October luncheon |  | Plan October luncheon | Hold October luncheon
Decide how many "buddies" will be needed and for how long
|  |  |  | Start looking for ways to enhance not as active members' experience |  | Select ways to enhance ways to enhance not as active members' experience

## Collaboration 1
AAUW Whatcom Branch
SMART Goal - Collaboration 1
In FY 20-21, we will increase our community visibility by collaborating with other organizations. To do this we will have a table at least six events held by other local organizations in Whatcom County.
We will co-sponsor at least one event with a local women’s organization such as League of Women Voters.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Have a table at six events held by other organizations in FY 20-21 and co-sponsor at least one event with another local women's org. | Put some funds into budget for co-sponsorship of event such as speaker | Brainstorm events to have table at | Select events to table | Agree on organization to sponsor event with and event | Advertise event | Continue planning event | Hold event
|  |  | Brainstorm organizations to collaborate with and what topics would be | Contact other organizations and assess level of interest | Begin planning event. Decide on date, obtain venue, agreement with event person
|  | end of March | end of April | name change announced | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
end of May

## Collaboration 2
AAUW Whatcom Branch
SMART Goal - Collaboration 2
In FY 20-21, we will increase our community visibility by assigning resources (money and staffing) to support at least four events hosted by other local organizations in Whatcom County.
We will ensure that a line item is put into our budget to provide funding for these events, and establish a committee to coordinate participation in each activity.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Support at least four events hosted by othr organizations. Ensure that we have line item in budget to fund and establish committee to coordinate | Money in budget | Brainstorm organizaitons and events | Select 1 event and notify organization. Provide funding | Select 1 event and notify organization. Provide funding | Select 1 event and notify organization. Provide funding |  | Select 1 event and notify organization. Provide funding
|  | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22

## Social Connections 1
AAUW Whatcom Branch
SMART Goal - Social Connections 1
In order to encourage social connections and build friendships, we will actively seek out input from our membership of what they are interested in doing together on a social level.
This will be accomplished through a survey to be conducted no later than the end of FY 19-20. In addition, by the end of FY 19-20, we will create and disseminate a New Member Interest form
to all new members going forward.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Seek membership input on social activities through survey by end of FY 19-20, and create New Member interest form and disseminate to all new members going forward | Create survey form - complete | Complete survey input via email | Compile survey results and recommend new interest groups. Work after this will be done by through Social Connect Goal #2
|  | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
Build new member letter survey that is complete
Add to new member communication packet (handbook, etc.)

## Social Connections 2
AAUW Whatcom Branch
SMART Goal - Social Connections 2
In order to better serve our membership and encourage social connections, we will increase the number and variety of activities for members to enjoy. By the end of FY 20-21, we will have at least
four interest groups with coordinators assigned. This will be accomplished by using the results of surveys and interest forms from Smart Goal #1 above, and by evaluating the effectiveness and
sustainability of our existing interest groups.
Action Plan for the Goal
Priority | SMART Goal | 1 month | 2 months | 3 months | 6 months | 9 months | 1 year | 1 1/2 years | 2 years
Metrics
Advocacy | Have four interest groups with coordinators by end of FY 20-21 | end of March | end of April | end of May | end of August | end of November | end of Feb 21 | end of August 21 | end of Feb 22
|  |  |  | Assess sustainability of existing interest groups | Solicit participants | Launch interest groups